## Project Planner
The three segments in these projects are image processing-based visualization, feature extraction and finally machine learning algorithms
Pothole Detection using Image processing & Machine Learning techniques |  |  |  |  | Period Highlight: | 50 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Ideation and brainstorming | 1 | 3 | 1 | 3 | 50%
Synopsis Submission | 4 | 5 | 4 | 5 | 100%
Image extraction and wrangling | 6 | 8 | 6 | 7 | 100%
Image processing : morphological transformation | 9 | 12 | 9 | 13 | 60%
Image processing : contours and convex hull | 13 | 13 | 13 | 14 | 45%
Image processing : contours dialation method | 14 | 16 | 14 | 15 | 100%
Image processing: conversion into hsv color space | 13 | 17 | 13 |  | 20%
Image processing: Image masking | 18 | 18 |  |  | 20%
Exploratory data analysis | 19 | 25 |  |  | 0%
Visual representations using matplotlib, seaborn | 25 | 25 |  |  | 0%
patching work | 26 | 26 |  |  | 0%
more image processing techniques exploration if unsatisfactory result | 27 | 29 |  |  | 0%
Deep learning concepts exploration in case we decide to move ahead with it | 30 | 35 |  |  | 50%
Extracting region of interest | 30 | 30 |  |  | 0%
Feature extaction | 30 | 34 |  |  | 0%
ML algorithm: SVM | 36 | 39 |  |  | 0%
ML algorithm: Decision tree | 36 | 41 |  |  | 0%
Final demonstartion and working checks | 42 | 42 |  |  | 0%
Final paper formulation | 42 | 43 |  |  | 0%
Tentative tasks | 44 |  |  |  | 0%